## Summary
Status | Name | Description | Note
0.75 | Firmware | update firmware for next rev of mainboard.
| satellite | see tasks tab
| host PC sw | see pc host tab
| db_cdh commands | see db_cdh tab
| cdh commands | see cdh tab
| website | see website tab
| ground station PC | see ground station tab

## Initial Work Plan
No. | People | Priority | Task | Personel Assignment | Notes
PHASE1
1 | 2 | Very high | Define / code simlation and data interface to host pc | Eric Tang, Bryce Putman | Make it fairly easy to add new dispays and simulated values
2 | 2 | High | Payload coding, definition, state machine design, etc. | Noah Carney, Noah Brodke | Prioritize function while simulation is being kinked out
3 | 2 | High | ADCS coding, definition, state machine design, etc. | Eric Tang, Bryce Putman | Refer to cryocube code. Working on this in parallel with #1 will probably help both tasks' completion
| 1 | high | Code real time debug display of actual/simulated telemetry, sensor, and payload data via USB
4 | PHASE 2
5 | 2 | high | Code host pc simulation functions for ADCS, payload dynamics during ADCS also
|  | high | Simulate payload arm dynamics for torques
5 |  |  | Continue Payload (step 2)
6 |  |  | Continue ADCS (step 3)
7

## Minimum Functinal Goal
Status | Name | Requirement
Move arm from lora command
take and send picture over lora
read sent telem over LoRa
operate payload at a target of 1hz images and 10hz arm control input.
have a live telemetry display on host pc
be able to simulate basic values from host pc
implement a video-like compression to payload camera to get a higher framerate at intended RF attenuation

## tasks
Status | Task | Description | Requirements | Priority | Frequency (Hz) | Time to Execute | Flight? | Notes
0 | adcs_task | big task for attitude control system. | see ADCS task tab | 2 |  |  |  | big state machine, I expect this to interact with other tasks as well.
1 | usb_debug_task | polls usb port for debug command input. | reads ascii encoded data from usb_cdc.data usb port. Make this also take tasks from the cdh file | 3 | 1 |  | No | Add extra commands to db_cdh.py as needed
1 | blink_task | Blinks on-board led |  | 3 | 0.5 |  | No
0.75 | imu_task | samples IMU on pycubed board | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1 |  |  | used this to verify IMUs. The xyz coordinates need to be switched around to match the sat. this and the libraries are a mess and need cleaned up
0.5 | battery_task | polls battery and currents to/from it. Sets low battery mode | disables/enables low battery mode where all devices are off | 1 | 0.1 |  |  | still has original files, wont be fully functional till next board rev
1 | time_task | prints time in terminal |  | 3 | 1
0 | temperature_task | polls device temperatures. Turns specific devices off if overtemp is detected |  | 2 | 0.1
0.25 | payload_task | payload operation task. | see payload_task tab | 3 | ? |  |  | big state machine and stuff
0.5 | gps_task | reads gps data | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1
0 | irridium_task | irridium beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
0.25 | lora_task | lora beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
1 | gc_task | garbage collector task
1 | template_task | parent task to all child tasks
0 | housekeeper_Task | various housekeeper functions, i.e. daily hreset, error handling, etc…
0 | startup_task | initial startup task | [5 empty] | original pycubed files, needs to be separated from irriduim and lora
marek wrote this, working thru what it does
marek wrote this, working thru what it does

## ADCS task
Status | Name | Description | Requirements: | Notes

## payload task
Status | Description | Requirements: | Notes
1 |  | define initial payload interface
1 |  | define initial payload task flow
0 |  | get initial implementation working
receive photo over usb
receive photo over LoRa
move arm over USB
move arm over LoRa
|  | refine interface for minimum bitrate 2kb/s min. MAX is 10kb/s | LoRa, bits not Bytes
evaluate implementing a video/like compression to the transmitted photo, to try to increase possible fps
goal is real time

## lora task
Status | Description | Requirements: | Notes
1 |  | Define initial data interface
1 |  | Define initial task flow
0 |  | get initial implementation working
0.5 |  | header for how many bytes in this packet
0.5 |  | header for number of packets
0.5 |  | Persistent settings stored on Flash. Default settings stored in program data.
0 |  | listen_again flag
multi-packet flag
other flags?
evaluate send_fast() opposed to send for payload
evaluate operation of data streaming down at in-flight attenuation
Evaluate LoRa internal CRC and implementing our own crc32 at the end of each packet

## libs
Status | Name | Description | Requirements: | Notes
0.9 | ad7091.py | device lib
1 | adafruit_gps.py | device lib |  | From pycubed so avoid editing if nessesary
1 | adm1176.py | device lib |  | From pycubed so avoid editing if nessesary
1 | bitflags.py | bit flag lib |  | From pycubed so avoid editing if nessesary
1 | bq25883.py | device lib |  | From pycubed so avoid editing if nessesary
1 | debugcolor.py | usb debug interface lib |  | Avoid editing if nessesary
0.75 | foras_promineo_payload.py | board-level lib
0.9 | foras_promineo_pib.py | board-level lib
0.9 | iam20380.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | max7311.py | device lib
0.9 | mcp47fvb24.py | device lib
0.9 | mmc5983.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | mxc6655.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | pca9543.py | device lib
0.75 | pycubed.py | pycubed master library |  | Edit for next rev of mb
1 | pycubed_rfm9x.py | lora radio library. |  | From pycubed so avoid editing if nessesary
0 | rockblock_9603.py | interfacing rockblock
0.9 | sli_imu.py | interfacing the IMUs |  | kindof a mess right now. Needs cleaned up
0.5 | config.py | loads settings for a task, settable via cdh |  | unverified
Feel free to add as nessesary, but try to avoid bloat.

## db_cdh
Status | Command | Description | Args | Notes
1 | no-op | returns ACK
1 | hreset | hard reset of board |  | see pycubed docs
1 | query | preforms eval(args) |  | see pycubed docs
1 | exec_cmd | preforms exec(args) |  | see pycubed docs
1 | get_imu_offset | prints IMU device offset over (args) samples | number of samples to avg
| cfg_upload | upload a new config for a task
ADCS_calibrate
| CRC | crc something
| print_file | prints file | path | this function is in pycubed.py already so maybe just call it?
| ls | shows files and folders on SD | path
send_log
| delete | delete file (x)

## cdh
Status | Command | Description | Args | Notes
1 | no-op | returns ACK
0.5 | hreset | hard reset of board |  | see pycubed docs, add security
0.5 | query | preforms eval(args) |  | see pycubed docs, add security
0.5 | exec_cmd | preforms exec(args) |  | see pycubed docs, add security
| start_payload | starts payload mode
| stop_payload | stops payload mode
| connect | connects, stopping beacon and listening more
| disconnect | disonnects
| payload_cmd | sends arm commands to payload
| payload_img | requests img from payload
CRC
print_file
ls
send_log
cfg_edit
delete
upload
merge / append

## pc host software
Status | Name | Description | Requirements: | Notes | Assigned
0 |  |  | define classes for gui and simulated objects to make creating new ones easy
0 |  |  | define classes for radio comms via a LoRa radio plugged into the host pc
0 | displaying live sensor , telemetry, and execution data | displaying live sensor data | Logging all terminal data from sessions. Timestamping data in log. | this will be primarily reading from the usb_debug terminal, no querying.
0 |  |  | ability to save enviornment variables and data for reloading
0 |  | ADCS sensor data, attitude rates (spacecraft dynamics)
0 |  | spacecraft orientation
0 |  | magnetic field (a function of position and orientation)
0 |  | GPS data (spacecraft position)
0 |  | star field for star tracker
0 |  | camera data | may have to be on a query basis unless in payload operation mode
0 |  | zero-g gameplay
0 | Simulate attiude and sensor inputs |  | non-intrusive to flight software, no possibility of entering to debug mode during flight. Operation frequency/speed should be close if not exact to flight execution. User can input the simlated data on the terminal from set scenarios entry.
0 |  | simulating ADCS sensor data, attitude rates (spacecraft dynamics)
0 |  | simulating spacecraft orientation
0 |  | simulating magnetic field (a function of position and orientation)
0 |  | simulating GPS data (spacecraft position)
0 |  | simulate star field for star tracker (function of position and orientation)
0 |  | simulate camera data (function of position, orientation, and dynamics)
0 |  | simulate zero-g gameplay
0 | provide CLI and/or GUI
0 | Use with ground antenna | LoRa radio will be plugged into a COM port also, so read/send data to that also
0 | additional peripheral device for controlling discrete signsl i/ps to bus, i.e. sep switches and reset | TBR
0 |  |  | 1fps, 10hz update payload operation over LoRa
0 |  |  | 1fps, 10hz update payload operation over USB

## bugs
Status | Name | Description | Solution | Notes
detected | i2c_bus dropout | i2c bus gets hung up[ after x seconds | implement and i2c_reset procedure. Needs to reinit all i2c devices on bus. Figure out what device is bringing the bus down….