## TODO
Priority | Name | Description | Note | Assigned
1 | Update pycubed.py | update libraries for next rev of mainboard. Add empty defs for things not implemented yet. |  | Caden
2 | Update firmware | update firmware for next rev of mainboard. |  | Caden
code tasks
code host PC debug sw

## tasks
Status | Task | Description | Priority | Frequency (Hz) | Time to Execute | Flight? | Notes
not started | adcs_task | big task for attitude control system. | 2 |  |  |  | big state machine, I expect this to interact with other tasks as well.
Done | usb_debug_task | polls usb port for debug command input | 3 | 1 |  | No | Add extra commands to db_cdh.py as needed
Done | blink_task | Blinks on-board led | 3 | 0.5 |  | No
In progress | imu_task | samples IMU on pycubed board | 2 | 1 |  |  | used this to verify IMUs. The xyz coordinates need to be switched around to match the sat.
In progress | battery_task | polls battery and currents to/from it. Sets low battery mode | 1 | 0.1 |  |  | still has original files, wont be fully functional till next board rev
Done | time_task | prints time in terminal | 3 | 1
not started | temperature_task | polls device temperatures. Turns specific devices off if overtemp is detected | 2 | 0.1
not started | payload_task | payload operation task. | 3 | ? |  |  | big state machine and stuff
in progress | gps_task | reads gps data | 2 | 1
not started | irridium_task | irridium beacon and radio up/downlink | 2 | ?/variable
not started | lora_task | lora beacon and radio up/downlink | 2 | ?/variable
N/A | beacon | [5 empty] | original pycubed files, needs to be separated from irriduim and lora
N/A | test
N/A | test_task
| communication | [5 empty] | marek wrote this, working thru what it does
| game_manager | [5 empty] | marek wrote this, working thru what it does

## db_cdh
Status | Command | Description | Args | Notes
Done | no-op | returns ACK
Done | hreset | hard reset of board |  | see pycubed docs
Done | query | preforms eval(args) |  | see pycubed docs
Done | exec_cmd | preforms exec(args) |  | see pycubed docs
in progress | get_imu_offset | prints IMU device offset over (args) samples | number of samples to avg | how would I calculate offset for the magnetometer?
| print_file | prints file | path
| ls | shows files and folders on SD | path

## cdh
Status | Command | Description | Args | Notes
Done | no-op | returns ACK
Done | hreset | hard reset of board |  | see pycubed docs
Done | query | preforms eval(args) |  | see pycubed docs
Done | exec_cmd | preforms exec(args) |  | see pycubed docs