## Minimum Functinal
Status | Name | Requirement
Move arm from lora command
take and send picture over lora4
read WASD and send over LoRa at X frequency on host PC
poll LoRa at x frequency for command input
send LoRa WASD data to openMV
Command OpenMV to take and send a photo
send Photo over LoRa for host PC to read on it's LoRa reciever

## TODO
Status | Priority | Name | Description | Note | Assigned
|  | Update pycubed.py | update libraries for next rev of mainboard. Add empty defs for things not implemented yet. |  | Caden
|  | Update firmware | update firmware for next rev of mainboard. |  | Caden
|  | code tasks | see tasks tab
|  | code host PC sw | see pc host tab
|  | code db_cdh commands | see db_cdh tab
|  | code cdh commands | see cdh tab
|  | code website | see website tab
|  | code ground station PC | see ground station tab

## Initial Work Plan
No. | People | Priority | Task | Personel Assignment | Notes
PHASE1
1 | 2 | Very high | Define / code simlation and data interface to host pc | Eric Tang, Bryce Putman
2 | 2 | High | Payload coding, definition, state machine design, etc. | Noah Carney, Noah Brodke | High-level functionality is prioritized. Prioritize design while simulation is being kinked out
3 | 2 | High | ADCS coding, definition, state machine design, etc. | Eric Tang, Bryce Putman | High-level functionality is prioritized. Refer to cryocube code also. Working on this in parallel with #1 will probably help both tasks' completion
PHASE 2
4 | 1 | high | Code real time debug display of actual/simulated telemetry, sensor, and payload data via USB |  | if Unity works out, display debug values and visuals?
5 | 2 | high | Code host pc simulation functions for ADCS, payload dynamics during ADCS also |  | look into physics sim in unity with Python API
|  | high | Simulate payload arm dynamics for torques |  | look into physics sim in unity with Python API
5 |  |  | Continue Payload (step 2)
6 |  |  | Continue ADCS (step 3)
7

## tasks
Status | Task | Description | Requirements | Priority | Frequency (Hz) | Time to Execute | Flight? | Notes
0 | adcs_task | big task for attitude control system. | see ADCS task tab | 2 |  |  |  | big state machine, I expect this to interact with other tasks as well.
Done | usb_debug_task | polls usb port for debug command input. | reads ascii encoded data from usb_cdc.data usb port. Make this also take tasks from the cdh file | 3 | 1 |  | No | Add extra commands to db_cdh.py as needed
Done | blink_task | Blinks on-board led |  | 3 | 0.5 |  | No
In progress | imu_task | samples IMU on pycubed board | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1 |  |  | used this to verify IMUs. The xyz coordinates need to be switched around to match the sat. this and the libraries are a mess and need cleaned up
In progress | battery_task | polls battery and currents to/from it. Sets low battery mode | disables/enables low battery mode where all devices are off | 1 | 0.1 |  |  | still has original files, wont be fully functional till next board rev
not started | lowbatt_task | critical functions to be preformed during low battery operation | beacon, look for cdh to remove low batt, etc. may be merged with battery_task.
Done | time_task | prints time in terminal |  | 3 | 1
not started | temperature_task | polls device temperatures. Turns specific devices off if overtemp is detected |  | 2 | 0.1
not started | payload_task | payload operation task. | see payload_task tab | 3 | ? |  |  | big state machine and stuff
in progress | gps_task | reads gps data | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1
not started | irridium_task | irridium beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
not started | lora_task | lora beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
done? | gc_task | garbage collector task
| template_tasl | parent task to all child tasks
N/A | beacon | [6 empty] | original pycubed files, needs to be separated from irriduim and lora
N/A | test
N/A | test_task
N/A | communication | [6 empty] | marek wrote this, working thru what it does
N?A | game_manager | [6 empty] | marek wrote this, working thru what it does

## ADCS task
Status | Name | Description | Requirements: | Notes
Persistent settings stored on SD. Default settings stored in program data.

## payload task
Status | Name | Description | Requirements: | Notes
Persistent settings stored on SD. Default settings stored in program data.
State machine for payload operation defined
|  |  | Data interfaces and transactopns defined for minimum bitrate 2kb/sec min. MAX is 15kb/s TBR | LoRa, bits not Bytes
modifying other task settings during this
define a "frame" of what data is sent over x time
goal is real time

## lora_irridium_task
Status | Name | Description | Requirements: | Notes
Define data interface
CRC
header for how many bytes in this packet
header for number of packets
Persistent settings stored on SD. Default settings stored in program data.
listen_again flag
deep sleep?
rapid OTA?

## libs
Status | Name | Description | Requirements: | Notes
in progress | ad7091.py | device lib
finished | adafruit_gps.py | device lib |  | From pycubed so avoid editing if nessesary
finished | adm1176.py | device lib |  | From pycubed so avoid editing if nessesary
finished | bitflags.py | bit flag lib |  | From pycubed so avoid editing if nessesary
finished | bq25883.py | device lib |  | From pycubed so avoid editing if nessesary
finished | debugcolor.py | usb debug interface lib |  | Avoid editing if nessesary
in progress | foras_promineo_payload.py | board-level lib
in progress | foras_promineo_pib.py | board-level lib
finished | iam20380.py | device lib |  | kind of a mess right now. Needs cleaned up
in progress | max7311.py | device lib
in progress | mcp47fvb24.py | device lib
finished | mmc5983.py | device lib |  | kind of a mess right now. Needs cleaned up
finished | mxc6655.py | device lib |  | kind of a mess right now. Needs cleaned up
finished | pca9543.py | device lib
always room for improvement | pycubed.py | pycubed master library |  | Avoid editing if nessesary
implement proper logging and debug stuff
finished | pycubed_rfm9x.py | lora radio library. |  | From pycubed so avoid editing if nessesary
not started | rockblock_9603.py | interfacing rockblock
in progress | sli_imu.py | interfacing the IMUs |  | kindof a mess right now. Needs cleaned up
? | smart_buffer.py |  |  | not sure purpose of this
| settings_loader.py | loads settings for a task, not default values coded in.
Feel free to add as nessesary, but try to avoid bloat.

## db_cdh
Status | Command | Description | Args | Notes
Done | no-op | returns ACK
Done | hreset | hard reset of board |  | see pycubed docs
Done | query | preforms eval(args) |  | see pycubed docs
Done | exec_cmd | preforms exec(args) |  | see pycubed docs
in progress | get_imu_offset | prints IMU device offset over (args) samples | number of samples to avg | how would I calculate offset for the magnetometer?
| CRC | crc something
| print_file | prints file | path | this function is in pycubed.py already so maybe just call it?
| ls | shows files and folders on SD | path
send_log
| SET_X | edits persistent setting (X)
| delete | delete file (x)
| upload | upload file (252 bytes max)
| merge / append | merge files sent over previous transmissions
MAKE DB_CDH

## cdh
Status | Command | Description | Args | Notes
Done | no-op | returns ACK
Done | hreset | hard reset of board |  | see pycubed docs, add security
In progress | query | preforms eval(args) |  | see pycubed docs, add security
In progress | exec_cmd | preforms exec(args) |  | see pycubed docs, add security
CRC
print_file
ls
send_log
SET_X
delete
upload
merge / append
start_payload
send_payload_data

## pc host software
Index | Priority | Name | Description | Requirements: | Notes | Assigned
|  | displaying live sensor , telemetry, and execution data | displaying live sensor data | Logging all terminal data from sessions. Timestamping data in log. | this will be primarily reading from the usb_debug terminal, no querying.
ability to save enviornment variables and data for reloading
ADCS sensor data, attitude rates (spacecraft dynamics)
spacecraft orientation
magnetic field (a function of position and orientation)
GPS data (spacecraft position)
star field for star tracker
|  |  | camera data | may have to be on a query basis unless in payload operation mode
zero-g gameplay
|  | Simulate attiude and sensor inputs |  | non-intrusive to flight software, no possibility of entering to debug mode during flight. Operation frequency/speed should be close if not exact to flight execution. User can input the simlated data on the terminal from set scenarios entry.
simulating ADCS sensor data, attitude rates (spacecraft dynamics)
simulating spacecraft orientation
simulating magnetic field (a function of position and orientation)
simulating GPS data (spacecraft position)
simulate star field for star tracker (function of position and orientation)
simulate camera data (function of position, orientation, and dynamics)
simulate zero-g gameplay
provide CLI and/or GUI
|  | Use with ground antenna | TBR
additional preifpherial device for controlling discrete signsl i/ps to bus, i.e. sep switchgs and reset

## bugs
Status | Name | Description | Solution | Notes
detected | i2c_bus dropout | i2c bus gets hung up[ after x seconds | implement and i2c_reset procedure. Needs to reinit all i2c devices on bus since .deinit procedure also deletes the object i2c