## Design Changes
Make manufacturer put no solder on unused pads
Make manufacturer assemble all parts even if we have to cosign them, these boards are challenging to assemble

## FP-P-01
Board Location: | SLI TDEC in Foras Promineo ESD tote
Date | Action | Comment | Date | Todo | Comment
2022-02-16 | Received |  | 2022-02-17 | Place C201 C202 C204 C206 C207 C208 C209, They were accidently labeled as 0603 parts in the BOM. p/n rom backplane
2022-02-17 | Removed all unused pads’ solder |  | 2022-02-17 | Place R8
2022-02-17 | Placed U4, U5, U8, U203, U210, U211, | U210 looked a little sketchy | 2022-02-17 | Verify R13, 29 are placed
|  |  | 2022-02-17 | Verify Q221 and Q209
|  |  | 2022-02-17 | Place L1
|  |  | 2022-02-17 | Verify C242, C243, C245, C246, C247, C248 placement
|  |  | 2022-02-17 | Place U2
|  |  | 2022-02-17 | Place U4
|  |  | 2022-02-17 | Place U5
|  |  | 2022-02-17 | Place U8
|  |  | 2022-02-17 | Place U13 ?
|  |  | 2022-02-17 | Place U14 ?
|  |  | 2022-02-17 | Place U16
|  |  | 2022-02-17 | Place U17
|  |  | 2022-02-17 | Place U23, 24 ?
|  |  | 2022-02-17 | Place U203, U210
|  |  | 2022-02-17 | Place U204, U207
|  |  | 2022-02-17 | Place U211
|  |  | 2022-02-17 | L1, R8 buy | done

## FP-P-02
Board Location: | Caden
Date | Action | Comment | Date | Todo | Comment
2022-02-16 | Received |  | 2022-02-17 | Place C201 C202 C204 C206 C207 C208 C209, They were accidently labeled as 0603 parts in the BOM. p/n rom backplane
2022-02-17 | Removed all unused pads’ solder |  | 2022-02-17 | Place R8
2022-02-17 | Placed U4, U5, U8, U203, U210, U211, |  | 2022-02-17 | Verify R13, 29 are placed
|  |  | 2022-02-17 | Verify Q221 and Q209
|  |  | 2022-02-17 | Place L1
|  |  | 2022-02-17 | Verify C242, C243, C245, C246, C247, C248 placement
|  |  | 2022-02-17 | Place U2
|  |  | 2022-02-17 | Place U4
|  |  | 2022-02-17 | Place U5
|  |  | 2022-02-17 | Place U8
|  |  | 2022-02-17 | Place U13 ?
|  |  | 2022-02-17 | Place U14 ?
|  |  | 2022-02-17 | Place U16
|  |  | 2022-02-17 | Place U17
|  |  | 2022-02-17 | Place U23, 24 ?
|  |  | 2022-02-17 | Place U203, U210
|  |  | 2022-02-17 | Place U204, U207
|  |  | 2022-02-17 | Place U211
|  |  | 2022-02-17 | L1, R8 buy