## Summary
Status | Name | Description | Note
0.75 | Firmware | update firmware for next rev of mainboard.
| satellite | see tasks tab
| host PC sw | see pc host tab
| db_cdh commands | see db_cdh tab
| cdh commands | see cdh tab
| website | see website tab
| ground station PC | see ground station tab

## Initial Work Plan
No. | People | Priority | Task | Personel Assignment | Notes
PHASE1
1 | 2 | Very high | Define / code simlation and data interface to host pc | Eric Tang, Bryce Putman | Make it fairly easy to add new dispays and simulated values
2 | 2 | High | Payload coding, definition, state machine design, etc. | Noah Carney, Noah Brodke | Prioritize function while simulation is being kinked out
3 | 2 | High | ADCS coding, definition, state machine design, etc. | Eric Tang, Bryce Putman | Refer to cryocube code. Working on this in parallel with #1 will probably help both tasks' completion
| 1 | high | Code real time debug display of actual/simulated telemetry, sensor, and payload data via USB
4 | PHASE 2
5 | 2 | high | Code host pc simulation functions for ADCS, payload dynamics during ADCS also
|  | high | Simulate payload arm dynamics for torques
5 |  |  | Continue Payload (step 2)
6 |  |  | Continue ADCS (step 3)
7

## Minimum Functinal Goal
Status | Name | Requirement
0 | Move arm from lora command
0 | take and send picture over lora
0 | read sent telem over LoRa
0 | operate payload at a target of 1hz images and 10hz arm control input.
0 | have a live telemetry display on host pc
0 | be able to simulate basic values from host pc
0 | implement a video-like compression to payload camera to get a higher framerate at intended RF attenuation

## States
TO
FROM |  |  | safe |  |  | startup |  |  |  |  | idle |  | payload
|  |  | sleep | check batteries | sos beacon | init | deploy | adcs calibration | first radio comm | end startup | beacon | connected | init | receive | burst
| safe | sleep |  | time
|  | check batteries |  |  |  | if entered from startup |  |  |  |  | if entered from idle or payload
|  | sos beacon |  |  |  | completion
| startup | init | housekeeper |  |  |  | completion
|  | deploy | housekeeper |  |  |  |  | completion
|  | adcs calibration | housekeeper | [5 empty] | completion
|  | first radio comm | housekeeper | [6 empty] | completion
|  | end startup | housekeeper | [7 empty] | completion
| idle | beacon | housekeeper | [8 empty] | cmd
|  | connected | housekeeper | [7 empty] | timeout or cmd |  | cmd
| payload | init | housekeeper | [10 empty] | completion
|  | receive | housekeeper | [7 empty] | timeout | cmd |  |  | cmd
|  | burst | housekeeper | [10 empty] | end
TO
| FROM |  | safe | startup | idle | payload
safe
startup
idle
payload
automatic transition
NOTES
safe mode is an individual task that will stop all scheduled tasks and not leave itself untill safe mode is disengaged.
startup tasks is an individual task that will manage execution of several other tasks during the on-orbit startup procedure.
every state can transition to sleep because housekeeper_task.py (the task that triggers transition) should always be running. (except during safe)
the beacon to connected mode transition is initiated through a command.
connected and payload receive mode are identical EXCEPT that the payload has been commanded on
the connected mode to payload receive mode transition is initiated throgh a command.
the payload receive to beacon mode transition is initated throguh a command OR timeout
the payload receive to connected mode transition is initated throguh a command OR timeout
the payload receive to payload burst mode transition is initiated through a command
the payload burst to payload receive mode transition is initiated through the end of burst mode.

## Tasks
Status | Task | Description | Requirements | Priority | Frequency (Hz) | Time to Execute | Flight? | Notes
0 | adcs_task | big task for attitude control system. | see ADCS task tab | 2 |  |  |  | big state machine, I expect this to interact with other tasks as well.
1 | usb_debug_task | polls usb port for debug command input. | reads ascii encoded data from usb_cdc.data usb port. Make this also take tasks from the cdh file | 3 | 1 |  | No | Add extra commands to db_cdh.py as needed
1 | blink_task | Blinks on-board led |  | 3 | 0.5 |  | No
0.75 | imu_task | samples IMU on pycubed board | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1 |  |  | used this to verify IMUs. The xyz coordinates need to be switched around to match the sat. this and the libraries are a mess and need cleaned up
0.5 | battery_task | polls battery and currents to/from it. Sets low battery mode | disables/enables low battery mode where all devices are off | 1 | 0.1 |  |  | still has original files, wont be fully functional till next board rev
1 | time_task | prints time in terminal |  | 3 | 1
0 | temperature_task | polls device temperatures. Turns specific devices off if overtemp is detected |  | 2 | 0.1
0.25 | payload_task | payload operation task. | see payload_task tab | 3 | ? |  |  | big state machine and stuff
0.5 | gps_task | reads gps data | Persistent settings stored on SD. Default settings stored in program data. | 2 | 1
0 | irridium_task | irridium beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
0.25 | lora_task | lora beacon and radio up/downlink | see lora_irridium_task tab | 2 | ?/variable
1 | gc_task | garbage collector task
1 | template_task | parent task to all child tasks
0 | housekeeper_Task | various housekeeper functions, i.e. daily hreset, error handling, etc…
0 | startup_task | initial startup task | needs to start / end several other tasks |  |  |  |  | original pycubed files, needs to be separated from irriduim and lora
marek wrote this, working thru what it does
marek wrote this, working thru what it does

## adcs_task.py
Status | Name | Description | Requirements: | Notes

## payload_task.py
Status | Description | Requirements: | Notes
1 |  | define initial payload interface
1 |  | define initial payload task flow
0 |  | get initial implementation working
0 |  | receive photo over usb
0 |  | receive photo over LoRa
0 |  | move arm over USB
0 |  | move arm over LoRa
0 |  | refine interface for minimum bitrate 2kb/s min. MAX is 10kb/s | LoRa, bits not Bytes
0 |  | evaluate implementing a video/like compression to the transmitted photo, to try to increase possible fps
0 |  | goal is real time

## lora_task.py
Status | Description | Requirements: | Notes
1 |  | Define initial data interface
1 |  | Define initial task flow
0 |  | get initial implementation working
0.5 |  | header for how many bytes in this packet
0.5 |  | header for number of packets
0.5 |  | Persistent settings stored on Flash. Default settings stored in program data.
0 |  | listen_again flag
0 |  | multi-packet flag
0 |  | other flags?
0 |  | evaluate send_fast() opposed to send for payload
0 |  | evaluate operation of data streaming down at in-flight attenuation
0 |  | Evaluate LoRa internal CRC and implementing our own crc32 at the end of each packet

## irridium_task.py
Status | Description | Requirements: | Notes
0 |  | Define initial data interface
0 |  | Define initial task flow
0 |  | get initial implementation working
0 |  | header for how many bytes in this packet
0 |  | header for number of packets
0 |  | Persistent settings stored on Flash. Default settings stored in program data.
0 |  | listen_again flag
0 |  | multi-packet flag
0 |  | other flags?
0 |  | evaluate send_fast() opposed to send for payload
0 |  | evaluate operation of data streaming down at in-flight attenuation
0 |  | Evaluate LoRa internal CRC and implementing our own crc32 at the end of each packet

## libs
Status | Name | Description | Requirements: | Notes
0.9 | ad7091.py | device lib
1 | adafruit_gps.py | device lib
1 | adm1176.py | device lib
1 | bitflags.py | bit flag lib
1 | bq25883.py | device lib
1 | debugcolor.py | usb debug interface lib
0.75 | foras_promineo_payload.py | board-level lib
0.9 | foras_promineo_pib.py | board-level lib
0.9 | iam20380.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | max7311.py | device lib
0.9 | mcp47fvb24.py | device lib
0.9 | mmc5983.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | mxc6655.py | device lib |  | kind of a mess right now. Needs cleaned up
0.9 | pca9543.py | device lib
0.75 | pycubed.py | pycubed master library |  | Edit for next rev of mb
1 | pycubed_rfm9x.py | lora radio library. |  | From pycubed so avoid editing if nessesary
0 | rockblock_9603.py | interfacing rockblock
0.9 | sli_imu.py | interfacing the IMUs |  | kindof a mess right now. Needs cleaned up
0.5 | config.py | loads settings for a task |  | unverified

## db_cdh.py
Status | Command | Description | Args | Notes
1 | no-op | returns ACK | none
1 | hreset | hard reset of board | none
1 | query | preforms eval(args) | query | see pycubed docs
1 | exec_cmd | preforms exec(args) | exec | see pycubed docs
1 | get_imu_offset | prints IMU device offset over (args) samples | number of samples to avg | probably broken
| cfg_upload | upload a new config for a task | .bak file or ascii dictionary of values? | .bak file or ascii dictionary of values?
ADCS_calibrate
| CRC | crc something
| print_file | prints file | path | this function is in pycubed.py already so maybe just call it?
| ls | shows files and folders on SD | path
send_log
| delete | delete file (x)

## cdh.py
Status | Command | Description | Args | Notes
1 | no-op | returns ACK
0.5 | hreset | hard reset of board | make password protected! | see pycubed docs, add security
0.5 | query | preforms eval(args) | make password protected! | see pycubed docs, add security
0.5 | exec_cmd | preforms exec(args) | make password protected! | see pycubed docs, add security
| start_payload | starts payload mode
| stop_payload | stops payload mode
| connect | connects, stopping beacon and listening more
| disconnect | disconnects
| payload_cmd | sends arm commands to payload
| payload_img | requests img from payload
CRC
print_file
ls
send_log
cfg_edit
delete
upload
merge / append

## pc host software
Status | Name | Description | Requirements: | Notes | Assigned
0 |  |  | define classes for gui and simulated objects to make creating new ones easy
0 |  |  | define classes for radio comms via a LoRa radio plugged into the host pc
0 | displaying live sensor , telemetry, and execution data | displaying live sensor data | Logging all terminal data from sessions. Timestamping data in log. | this will be primarily reading from the usb_debug terminal, no querying.
0 |  |  | ability to save enviornment variables and data for reloading
0 |  | ADCS sensor data, attitude rates (spacecraft dynamics)
0 |  | spacecraft orientation
0 |  | magnetic field (a function of position and orientation)
0 |  | GPS data (spacecraft position)
0 |  | star field for star tracker
0 |  | camera data | may have to be on a query basis unless in payload operation mode
0 |  | zero-g gameplay
0 | Simulate attiude and sensor inputs |  | non-intrusive to flight software, no possibility of entering to debug mode during flight. Operation frequency/speed should be close if not exact to flight execution. User can input the simlated data on the terminal from set scenarios entry.
0 |  | simulating ADCS sensor data, attitude rates (spacecraft dynamics)
0 |  | simulating spacecraft orientation
0 |  | simulating magnetic field (a function of position and orientation)
0 |  | simulating GPS data (spacecraft position)
0 |  | simulate star field for star tracker (function of position and orientation)
0 |  | simulate camera data (function of position, orientation, and dynamics)
0 |  | simulate zero-g gameplay
0 | provide CLI and/or GUI
0 | Use with ground antenna | LoRa radio will be plugged into a COM port also, so read/send data to that also
0 | additional peripheral device for controlling discrete signsl i/ps to bus, i.e. sep switches and reset | TBR
0 |  |  | 1fps, 10hz update payload operation over LoRa
0 |  |  | 1fps, 10hz update payload operation over USB

## bugs
Status | Name | Description | Solution | Notes
detected | i2c_bus dropout | i2c bus gets hung up[ after x seconds | implement and i2c_reset procedure. Needs to reinit all i2c devices on bus. Figure out what device is bringing the bus down….